## Risk Register
Risk ID | Risk | Category | Probability | Impact | RMMM
R1 | Scope creep / requirements change | Scope | 50% | High | Change control; defined acceptance criteria; stakeholder sign-off; backlog grooming
R2 | Requirements ambiguity | Requirements | 45% | High | Refine user stories; acceptance tests; continuous stakeholder clarification
R3 | Stakeholder priority shifts | Stakeholder | 40% | Medium-High | Governance board; prioritized backlog; regular demos
R4 | Vendor / third-party failure | Vendor | 25% | High | Vendor SLAs; backup vendors; contractual penalties; integration tests
R5 | API / integration incompatibility | Technical | 40% | Medium-High | Early prototyping; contract tests; mocks; CI integration tests
R6 | Data quality / integrity issues | Data | 35% | High | Validation rules; ETL checks; data profiling; CI data tests
R7 | Security vulnerability / data breach | Security | 20% | Critical | Secure design; encryption; IAM; pen testing; logging/alerts
R8 | Regulatory / compliance change | Compliance | 15% | High | Regulatory monitoring; legal reviews; configurable controls
R9 | Performance / scalability limitations | Performance | 30% | High | Load testing; capacity planning; architectural reviews
R10 | Infrastructure / cloud outage | Infrastructure | 10% | High | Multi-AZ/region deployments; redundancy; failover tests
R11 | Deployment pipeline failure | DevOps | 25% | Medium | Pipeline health checks; blue/green or canary; rollback scripts
R12 | Insufficient automated testing | Quality | 35% | High | Increase unit/integration/e2e coverage; test gates in CI
R13 | Legacy system constraints | Legacy | 30% | Medium-High | Interface adapters; encapsulation; compatibility layers
R14 | Third-party dependency breaking change | Dependency | 30% | Medium | Pin versions; scheduled dependency updates; integration tests
R15 | License or cost increases | Financial | 20% | Medium | Budget buffer; re-evaluate alternatives; negotiate terms
R16 | Insufficient budget/funding cuts | Financial | 15% | High | Prioritized roadmap; MVP focus; cost forecasts
R17 | Optimistic estimation / schedule slippage | Schedule | 40% | Medium-High | Time buffers; decomposition; velocity tracking
R18 | Inadequate monitoring & observability | Ops | 35% | Medium-High | Implement tracing, metrics, alerts, runbooks
R19 | Configuration management errors | Ops | 25% | Medium | Immutable infrastructure; config as code; reviews
R20 | Environment drift (dev/stage/prod) | Ops | 30% | Medium | Use container images; identical infra as code; smoke tests
R21 | Low user adoption / usability issues | User | 30% | Medium | Usability testing; early user feedback; analytics
R22 | Data migration errors | Data | 20% | High | Migration dry-runs; validation checks; backups
R23 | Backup / disaster recovery failure | DR | 15% | Critical | Automated backups; restore drills; offsite copies
R24 | Intellectual property / licensing dispute | Legal | 10% | High | Legal review; indemnities in contracts; provenance checks
R25 | Security misconfiguration (IAM, S3, etc.) | Security | 22% | High | Automated config scanning; least privilege; audit logs

## R1_Scope creep - requirements c
Risk ID | Date | Probability | Impact
R1 | 2026-06-22 | 50% | High
Field | Details
Description | Uncontrolled changes to scope lead to schedule and cost overruns
Refinement / Context
Mitigation / Monitoring | Change control; defined acceptance criteria; stakeholder sign-off; backlog grooming
Management / Contingency plan / Triggers | Freeze scope or re-schedule features; sponsor escalation
Current status | Active - change-control in place

## R2_Requirements ambiguity
Risk ID | Date | Probability | Impact
R2 | 2026-06-22 | 45% | High
Field | Details
Description | Poorly defined requirements cause rework and defects
Refinement / Context
Mitigation / Monitoring | Refine user stories; acceptance tests; continuous stakeholder clarification
Management / Contingency plan / Triggers | Schedule clarification spike; defer unclear items
Current status | Monitoring - clarification workshops planned

## R3_Stakeholder priority shifts
Risk ID | Date | Probability | Impact
R3 | 2026-06-22 | 40% | Medium-High
Field | Details
Description | Changing business priorities disrupt roadmap
Refinement / Context
Mitigation / Monitoring | Governance board; prioritized backlog; regular demos
Management / Contingency plan / Triggers | Re-plan release scope; negotiate minimum viable features
Current status | Monitored - governance scheduled

## R4_Vendor - third-party failure
Risk ID | Date | Probability | Impact
R4 | 2026-06-22 | 25% | High
Field | Details
Description | Critical third-party service becomes unavailable or unsupported
Refinement / Context
Mitigation / Monitoring | Vendor SLAs; backup vendors; contractual penalties; integration tests
Management / Contingency plan / Triggers | Switch provider or local workaround; escalate contract
Current status | Controls defined

## R5_API - integration incompatib
Risk ID | Date | Probability | Impact
R5 | 2026-06-22 | 40% | Medium-High
Field | Details
Description | Integrations fail due to mismatched contracts or versions
Refinement / Context
Mitigation / Monitoring | Early prototyping; contract tests; mocks; CI integration tests
Management / Contingency plan / Triggers | Adapter layer; delay dependent features
Current status | Spike planned

## R6_Data quality - integrity iss
Risk ID | Date | Probability | Impact
R6 | 2026-06-22 | 35% | High
Field | Details
Description | Incorrect or inconsistent data leads to wrong business outcomes
Refinement / Context
Mitigation / Monitoring | Validation rules; ETL checks; data profiling; CI data tests
Management / Contingency plan / Triggers | Data cleansing job; hold releases that rely on bad data
Current status | Monitoring - profiling scheduled

## R7_Security vulnerability - dat
Risk ID | Date | Probability | Impact
R7 | 2026-06-22 | 20% | Critical
Field | Details
Description | Unauthorized access or exfiltration of sensitive data
Refinement / Context
Mitigation / Monitoring | Secure design; encryption; IAM; pen testing; logging/alerts
Management / Contingency plan / Triggers | Incident response plan; breach notification; forensics
Current status | Controls implemented; monitoring active

## R8_Regulatory - compliance chan
Risk ID | Date | Probability | Impact
R8 | 2026-06-22 | 15% | High
Field | Details
Description | New laws or regulations require product changes
Refinement / Context
Mitigation / Monitoring | Regulatory monitoring; legal reviews; configurable controls
Management / Contingency plan / Triggers | Compliance remediation sprint; notify stakeholders
Current status | Watched - legal subscribed

## R9_Performance - scalability li
Risk ID | Date | Probability | Impact
R9 | 2026-06-22 | 30% | High
Field | Details
Description | System cannot meet expected load or latency
Refinement / Context
Mitigation / Monitoring | Load testing; capacity planning; architectural reviews
Management / Contingency plan / Triggers | Scale-up infra; optimize code; delay ramp-up
Current status | Load tests scheduled

## R10_Infrastructure - cloud outa
Risk ID | Date | Probability | Impact
R10 | 2026-06-22 | 10% | High
Field | Details
Description | Cloud or hosting provider outage disrupts service
Refinement / Context
Mitigation / Monitoring | Multi-AZ/region deployments; redundancy; failover tests
Management / Contingency plan / Triggers | Failover to standby region; incident runbook
Current status | Redundancy in design

## R11_Deployment pipeline failure
Risk ID | Date | Probability | Impact
R11 | 2026-06-22 | 25% | Medium
Field | Details
Description | CI/CD failures prevent safe deployments
Refinement / Context
Mitigation / Monitoring | Pipeline health checks; blue/green or canary; rollback scripts
Management / Contingency plan / Triggers | Manual deploy procedures; hotfix branches
Current status | Pipeline monitoring active

## R12_Insufficient automated test
Risk ID | Date | Probability | Impact
R12 | 2026-06-22 | 35% | High
Field | Details
Description | Lack of tests increases defect escape to production
Refinement / Context
Mitigation / Monitoring | Increase unit/integration/e2e coverage; test gates in CI
Management / Contingency plan / Triggers | Introduce stricter QA cycles; hold release if critical bugs appear
Current status | Test coverage improvement plan

## R13_Legacy system constraints
Risk ID | Date | Probability | Impact
R13 | 2026-06-22 | 30% | Medium-High
Field | Details
Description | Old systems limit new feature implementations
Refinement / Context
Mitigation / Monitoring | Interface adapters; encapsulation; compatibility layers
Management / Contingency plan / Triggers | Refactor or isolate legacy components
Current status | Mitigation architecture drafted

## R14_Third-party dependency brea
Risk ID | Date | Probability | Impact
R14 | 2026-06-22 | 30% | Medium
Field | Details
Description | Library or SDK update breaks functionality
Refinement / Context
Mitigation / Monitoring | Pin versions; scheduled dependency updates; integration tests
Management / Contingency plan / Triggers | Patch or fork dependency; upgrade plan
Current status | Dependency policy enacted

## R15_License or cost increases
Risk ID | Date | Probability | Impact
R15 | 2026-06-22 | 20% | Medium
Field | Details
Description | Licensing or cloud costs rise unexpectedly
Refinement / Context
Mitigation / Monitoring | Budget buffer; re-evaluate alternatives; negotiate terms
Management / Contingency plan / Triggers | Reduce consumption; switch vendors
Current status | Budget monitoring active

## R16_Insufficient budget-funding
Risk ID | Date | Probability | Impact
R16 | 2026-06-22 | 15% | High
Field | Details
Description | Project funding reduced impacting deliveries
Refinement / Context
Mitigation / Monitoring | Prioritized roadmap; MVP focus; cost forecasts
Management / Contingency plan / Triggers | Scope reduction; seek additional funding
Current status | Roadmap prioritized

## R17_Optimistic estimation - sch
Risk ID | Date | Probability | Impact
R17 | 2026-06-22 | 40% | Medium-High
Field | Details
Description | Tasks take longer than estimated, slipping schedule
Refinement / Context
Mitigation / Monitoring | Time buffers; decomposition; velocity tracking
Management / Contingency plan / Triggers | Re-plan releases; negotiate dates
Current status | Velocity monitored

## R18_Inadequate monitoring & obs
Risk ID | Date | Probability | Impact
R18 | 2026-06-22 | 35% | Medium-High
Field | Details
Description | Lack of visibility delays detection and resolution
Refinement / Context
Mitigation / Monitoring | Implement tracing, metrics, alerts, runbooks
Management / Contingency plan / Triggers | Add temporary logging; increase telemetry retention
Current status | Observability backlog created

## R19_Configuration management er
Risk ID | Date | Probability | Impact
R19 | 2026-06-22 | 25% | Medium
Field | Details
Description | Wrong configuration causes outages or data loss
Refinement / Context
Mitigation / Monitoring | Immutable infrastructure; config as code; reviews
Management / Contingency plan / Triggers | Roll back configs; controlled change windows
Current status | IaC and review enforced

## R20_Environment drift (dev-stag
Risk ID | Date | Probability | Impact
R20 | 2026-06-22 | 30% | Medium
Field | Details
Description | Differences across environments cause unexpected failures
Refinement / Context
Mitigation / Monitoring | Use container images; identical infra as code; smoke tests
Management / Contingency plan / Triggers | Recreate environment; freeze deployments until fixed
Current status | Environment standardization in progress

## R21_Low user adoption - usabili
Risk ID | Date | Probability | Impact
R21 | 2026-06-22 | 30% | Medium
Field | Details
Description | Users do not adopt the product, reducing value
Refinement / Context
Mitigation / Monitoring | Usability testing; early user feedback; analytics
Management / Contingency plan / Triggers | UX improvements; adoption campaigns
Current status | User testing planned

## R22_Data migration errors
Risk ID | Date | Probability | Impact
R22 | 2026-06-22 | 20% | High
Field | Details
Description | Migration corrupts or loses data during transfer
Refinement / Context
Mitigation / Monitoring | Migration dry-runs; validation checks; backups
Management / Contingency plan / Triggers | Rollback to backup; manual remediation
Current status | Migration plan and tests prepared

## R23_Backup - disaster recovery
Risk ID | Date | Probability | Impact
R23 | 2026-06-22 | 15% | Critical
Field | Details
Description | Backups fail or cannot be restored when needed
Refinement / Context
Mitigation / Monitoring | Automated backups; restore drills; offsite copies
Management / Contingency plan / Triggers | Invoke disaster recovery playbook
Current status | DR drills scheduled

## R24_Intellectual property - lic
Risk ID | Date | Probability | Impact
R24 | 2026-06-22 | 10% | High
Field | Details
Description | IP claims or licensing conflicts disrupt delivery
Refinement / Context
Mitigation / Monitoring | Legal review; indemnities in contracts; provenance checks
Management / Contingency plan / Triggers | Cease contested features; legal action
Current status | Legal review available

## R25_Security misconfiguration (
Risk ID | Date | Probability | Impact
R25 | 2026-06-22 | 22% | High
Field | Details
Description | Incorrect security settings expose data or services
Refinement / Context
Mitigation / Monitoring | Automated config scanning; least privilege; audit logs
Management / Contingency plan / Triggers | Revoke keys; apply correct policies; incident response
Current status | Config scanning enabled